## Current Tasks
Sr.No. | TASK | Priority | Assigned | Backup | Start Development | End Development | Expected Duration | Status | Comment
1 | Seller Flow - Commission Percentage | High | Baba K | DattaPrasad | 3rd Jan 2022 |  | 30 Days | Development Started | Technical Plan DONE.
2 | Home Page API Integration | High | Yuvaraj P |  | 3rd Jan 2022 |  |  | Coordination with Mob Dev Team and API Integration Started at Mob Dev End
3 | AI Integration - Recommended | Normal | Sachin G |  | 31st Dec 2021 |  |  |  | Discussion with AI team going on
4 | Save customer product selection based on product and add to cart selection | High | Kaivalya M |  | 3rd Jan 2022 |  | 2 Days | Development in Progress
5 | Coupon Code Functionality - - Generate dynamic coupon code - Coupon Code as per usage 1) unlimited usage (lifetime); 2) one-time; 3) number of usage e.g. 3 - Admin, UI, API | High | Nisha M |  | 4th Jan 2022 |  |  |  | Technical Plan yet to start
6 | Admin - Export Manager - PDF/Excel/CSV | Normal | Baba K | Shubham |  |  |  |  | KT needed from Baba
7 | Admin - Import Manager - Category/Product/Brands/Filters/Images | Normal | Baba K | Shilpa C |  |  |  |  | KT needed from Baba/Onkar
8 | AI Reviews | Normal | Yuvaraj P/Vikas K | Kaivalya |  |  |  |  | Requirement Analysis
9 | Refund & Exchange | Normal | Sachin G
10 | Stock and Inventory | High | Kaivalya M | Sachin G |  |  |  |  | BRD document is ready and Tushar adding few points Technical Plan yet to Start
11 | Combo Offers | High | Kaivalya M | Omkar K | 4th Jan 2022 |  | 15-20 Days |  | Technical Plan is ready
12 | AI Advertisement | Normal | Kaivalya M
13 | PIM - Dynamic Catalog Management | High | [6 empty] | Tushar P need to revise documentation
14 | AI Integration - Top Trending | High | Sachin G
15 | QR Code Based Search Product | Normal | Shilpa C | Omkar Kadam
16 | Filter with Brand | Normal | Nisha M
17 | Home Page - Elastic Loader - Show products on scroll | Low | Poonam G | [5 empty] | Poonam got HTML design and started working using React.js
18 | Mantis Bug Fixes | Normal | Omkar K, Shilpa C | Shubham, DattaPrasad |  |  |  |  | Still in Progress. There are some old bugs. QA need to recheck and close
19 | We need to mask email and Phone number via web form. | Normal | Shilpa C
20 | As a admin user, I want to record the call notes so that other user would be able to see the same. | Normal | Omkar Kadam
21 | B2B Customer Login | Normal | Baba K | Shilpa C
22 | Dev Environment - To push updates for unit testing | Normal | Onkar J | [5 empty] | IT Support done with Setup.

## Adibuja Team
Senior .NET Developers | Junior .NET Developers | QA | React.js | Andriod | IOS | Xamarin
Yuvaraj P | Shilpa C | Ashutosh M | Poonam G | Achal B | Chaitrali C | Akashy K
Kaivalya M | Omkar Kadam | Mayuri P | Mayur S | Sanjay Dhakane |  | Kalyan P
Baba K | Milind S | Rahul Y |  | Abhay D
Sachin G | DattPrasad K
Nisha M | Shubham S
21 total count